## Sheet1
Who/What ? | Assumption | Risk
User adaptation | Users are expected to navigate on user interface | Interface may not be dislexia or other disability friendly
User experience | Some users will give a feedback of their experience | If no one does it, we won't be able to know software issues and fix them
User abilities | Users are expected to know how to do basic move on electronic devices | Project won't be beneficial for people without computer
Internet | Users, facility team and server side have a sufficient Internet connection | Our system won't be usable in locations with poor, unstable or missing Internet connection
Data accuracy | Users don't send false information through the software (false number of people or fake ID) | Risk of malicious attacks from competitors
External software | All external software linked to ours don't create issues with it | Process system depends on external software functionnality
Security | User's data is protected can't be accessible by someone else that the user | We need to constantly be aware of new security threats
Scalability | The system will grow as we go along | Bad planning of supply and demandmay cause overwhelmed served
Support | The system will require minimal ongoing maintenance, and support needs will be predictable | If the college IT team isn't sufficient, we need to find external assistance, causing additional money needed
Legal compliance | The system adheres to all relevant legal and compliance requirements | Changing laws could make the project irrelevant and inoperable