## Sheet1
Student Name:
| Project Plan | Weight | Mark | Comment
1 | Background | 5% | 0%
2 | Stakeholders | 5% | 0%
3 | Scope | 10% | 0%
4 | Deliverables | 5% | 0%
5 | Critical Assumptions | 5% | 0%
6 | Project Schedule including Work Breakdown Structure (WBS) in MS Project | 15% | 0%
7 | Roles And Responsibilities and Project Organization | 5% | 0%
8 | Budget | 10% | 0%
9 | Risk Management | 10% | 0%
10 | Quality | 5% | 0%
11 | Communication plan | 5% | 0%
12 | Methodology | 5% | 0%
13 | Presentation of the document, including format, general layout, spelling, grammar and clarity of communication | 15% | 0%
| Total | 100% | 0%